## Sheet1
Simple Work Breakdown Structure (Project Schedule) Template
Task ID | Task Description | Dependency | Start | Finish | Resource(s) | % Complete/Status
| Title (Example): Make Coffee |  | 7:00 | 7:25
Project Plan Check Up (assigned by Governing Body)
1 | Determine who wants coffee |  | 7:00 | 7:02
2 | Determine how much coffee is needed | 1 | 7:02 | 7:04
3 | Put water in coffee maker | 2 | 7:05 | 7:07
4 | Put coffee grounds in coffee maker | 2 | 7:05 | 7:07
5 | Starting brewing coffee | 3,4 | 7:07 | 7:07
6 | Monitor coffee's progress | 5 | 7:07AM | 7:17
7 | Pour coffee for each person | 6 | 7:17 | 7:20
8 | Wash coffee pot | 7 | 7:20 | 7:25